## Assumptions (EPD)
Instructions: Please enter your function's name and capture assumptions applicable to your sizing
Team Name / Function | Scope / Deliverables | Assumptions | Risks
Platform Security FW | 1. UBU /LibROM 2. ART FW / ASP FW / Manufacturing FW 3. Content Security: HDCP2.2 and WV | For LibROM: 1. enabling of Eris / SEC3.5 features 2. If FIPS certification is required, embedded team will take over after AFE For Security FW: 1. ART FW / UBU / ASP FW / Manufacturing - enabling of exisiting features 2. No XSP 3. No change in HDCP feature comparing to previous/roadmap programs. No change in WV (WV will be based on amd vcn ip and not brighton, otherwise effort estimate will increase significantly) 4. PFO leads Content Protection (WV and HDCP) post-UU as it was done on KRK2e 5. FuSA and ASIL B by BU if any 6. The majority of the effort for UBU and LibROM is focused on the pre-silicon phase. There will be some follow-up work after bring-up, primarily for full validation of features at the SoC level, as well as potential ROM patches or LibROM overlay deliveries to address ROM issues or work around RTL-related issues.
SPG_MM_Audio | Scope of Work: • Reuse of Medusa ACP 7.3a (AAF2.0 & Client Linux leverage) • Delta: o SW ASILB support:  Audio chimes  ACP monitored by safety island o HW ASRC: Need to confirm with program – WIP. Note: For the base support we can leverage deliverables to automotive. FUSA and ASRC are prilim right now, will adjust the HC in future based on the final mPRS and the scope of FUSA work. | 1. SW ASILB & HW ASRC are required as per the priliminary understanding. 2. Legacy reuse
3D Graphics and Compiler Team |  | Assumptions: 1. We're moving forward with Open Sourced XGL & OGLP, which under Jeff W's organization instead of under Rodney's organization. 2. We're running this product on Linux & RTOS, no windows support for this program Therefore, there's no PAL work, no Graphics Compiler work, nor there is proprietary XGL & OGL work
SPG_Display NPI | Scope of Work (Linux Only): 1. Pre-Si + Post-Si baseline + DQE + CI 2. VPE based virtual HW plane (Dedicated VPE engine for virtual HW plane solution. Not support video processing (AT) use cases via VPE) | 1. Virtual HW plane data path protection sizing is based on the proposed solution from DCN HW team. Need to rescope if the solution changes
SPG_MM_Video NPI | Leverage NVE version, that was bring up on Windows, is reused. NVE 1.3 will be used for Capitola. Capitola is the first to use this 1 core config of NVE NVE 1.3 FW and MMCore support for Linux upstream. Feature set scope is below: . HEVC / AVC / AV1 4:2:0 encode and decode . AV2 4:2:0 decode TBD . H.264 / H.265 4:2:2 encode and decode . H.264 / H.265 / AV2 4:4:4 encode and decode . Encode: Single-core, 4K-only . Decode: Single-core, 4K-only . No DCTD (no DNx decode) . No JPEG decode . No VPP . No MEE_ML . No MEE_Video | 1. Linux only 2. No RAS/ASILB for NVE
SPG_MM Video NTI | UES feature validation, bringup/debug support UES ASILB support for functinal safety | QoS policies is transparant to MM in the new internal VPE->DCN pipeline
RLC Firmware | Leverage Grimlock, Eris. | Feature set for Capitola is not currently known. Sizing assumes significant deltas from Grimlock and Eris. New RLC FW required and program validation support. Post SI support will be transitioned to BU at AFE.
CP Firmware | Based on Grimlock | Minor updates. Support for debug and bringup. Post SI support will be transitioned to BU at AFE.
PMFW | Leverage Medusa, Eric, Grimlock | Pre-si development only. Post-si work is executed by the business unit.
Core Linux | Linux Bringup & Pre-Si Emulation: - Pre-SI Emulation - Pre-SI Linux Bringup - Linux Bringup (Silicon) with Base kernel Graphics API : - Mesa, OpenGL 4.6, OpenGL ES 3.2, Vulkan-1.4 (Baremetal issue debug) Kernel support: - Kernel Consultation support | Graphics : - OpenGL SC is deprecated and is explicitly out of scope. - There is no clarity from the program side on the VulkanSC requirement. No sizing has been done until we get the clarity. Kernel : - Kernel related consultation. | Does VulkanSC needs the GPU driver to be safety complaint ? Any new work w.r.t VulkanSC needs rescoping.
Advanced Technologies Group | -Program Management: Manage Capitola board delivery, Linux dependencies, Android bringup, xTS resolution -Architecture: Architecture support and technical guidance for Capitola platform - GNPU: Graphics performance analysis and ML workload analysis/optimization - Android VAS3.0: Deliver Android Automotive features -Robotics SW/Usecases: Deliver Robotics SW stack and end-customer use-cases including simulator HW acceleration - FuSA: ISO26262 functional safety guidance for ASIL-B compliance - DevOps + Validation/QA: Platform validation and quality assurance, CI build pipeline setup and maintenance | - HC sizing is based on analogous programs (Fairview, Glacier Peak, GLK) since specific use-cases aren't yet available - Component teams own UMD, Compiler, and KMD delivery - Component teams own FuSa ASIL-level scoping/sizing for their modules. ATG scoping constrained to guidance/consulting only - Balanced ownership of full system validation split between ATG and other teams | -Pre‑silicon VAS3.0 stack non-availability will delay Android bring‑up -Unclear validation ownership across teams -HC sizing uncertainty due to limited use‑case definition -Dependency risk from component team deliverables
SPG_SPIO | Leverage Medusa, Eris, Grimlock, Krackan - MPIO, MPDACC, OpenSIL, ESID, PFQ | `- XGBE is leveraged from KRK, new PHY integration - Eris is baseline for other components - Fusa aspects not in scope / no impact to these components - Leverage Eris MEM PHY with 48b + Single Row Support - PCIE IDE support is new addition to Eris - Minimal support (consultation only) after bringup (focus on Build Infrastructure, MEM and MPIO)
Pre-Si FW Prg Mgr | FW program execution (HLD → AFE) by owning integrated plans, dependency mapping (FW, emulation, SimNow, DV), risk identification/closure, and executive readiness reporting to ensure feature enablement and milestone exit criteria are met across all pre-silicon workstreams |  | Pre-Si execution is gated by alignment of models, validation, requirements, and cross-functional dependencies—any slip directly blocks FW readiness and milestone exits.
PMFW | Leverage Medusa, Eric, Grimlock | Pre-si development only. Post-si work is executed by the business unit.

## Capitola C40 v1.0 r2 (EPD)
Sizing is OPEN. Please UPDATE your estimates for your teams in this sheet. Also UPDATE the scope, assumptions and risks in the Assumptions tab. | [38 empty] | Status
Capitola C40 v1.0 r2 (EPD) |  |  | Notes: BU - AECG - incorporate the updated R&R scope work-split with EPD and G&E SW | [35 empty] | In Progress
Last Updated |  | 2026-06-22 | Schedule Milestones>> | [7 empty] | LSA | LSB | LSC | LSD | BTO | UU |  |  |  |  | IP
|  |  | Resource Allocation |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 15.1 | 4 | 12978.6748 | 455087.5677
Category | Leader | Top Level Team | Function / Contact | Location | Allocation File | HC Type | Q126 | Q226 | Q326 | Q426 | Q127 | Q227 | Q327 | Q427 | Q128 | Q228 | Q328 | Q428 | Q129 | Q229 | Q329 | Q429 | Q130 | Q230 | Q330 | Q430 | Q131 | Q231 | Q331 | Q431 | Q132 | Q232 | Q332 | Q432 | Sum HC | Peak HC | Rate | Cost | HC Profile (mini) | Check
PFO | Chris | SPG_FWProgMgmt | Pre-Si Sys FW PM | Canada | alloc_PFO_PM_Arch | Incremental - XCHG |  |  | 0.75 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 | [17 empty] | 8.5 | 1 | 30138.2495 | 256175.1209
PFO | Chris | SPG_Platform Security | UBU / LibROM | Canada | alloc_PSPSecurity_MKM | Incremental - XCHG |  |  |  |  | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1 | [17 empty] | 8 | 1.5 | 30138.2495 | 241105.9961
PFO | Chris | SPG_Platform Security | ART FW / ASP FW / Manufacturing FW | Canada | alloc_PSPSecurity_MKM | Incremental - XCHG |  |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | [18 empty] | 11 | 2 | 30138.2495 | 331520.7447
PFO | Chris | SPG_Platform Security | Content Security (WV/HDCP) | Canada | alloc_PSPSecurity_MKM | Incremental - XCHG | [5 empty] | 1 | 1 | 2 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 1 | 0.5 | [12 empty] | 19.5 | 2.5 | 30138.2495 | 587695.8655
PFO | Chris | SPG_PMFW | PMFW | Canada | alloc_PMFW | Incremental - XCHG | [5 empty] | 2 | 2 | 2 | 2 | 2 | 1 | [17 empty] | 11 | 2 | 30138.2495 | 331520.7447
PFO | Chris | SPG_SPIO | ICTFW | Canada | alloc_SPIO | Incremental - XCHG |  |  |  |  | 1.5 | 3 | 3 | 3 | 3 | 3 | 0.5 | 0.5 | 0 | [15 empty] | 17.5 | 3 | 30138.2495 | 527419.3665
PFO | Chris | SPG_SPIO | OpenSIL + PFQ | Canada | alloc_SPIO | Incremental - XCHG |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | [16 empty] | 14 | 2 | 30138.2495 | 421935.4932
PFO | Chris | SPG_SPIO | MEM + DF | Canada | alloc_SPIO | Incremental - XCHG |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 0.5 | 0.5 | [16 empty] | 19 | 3 | 30138.2495 | 572626.7408
PFO | Chris | SPG_VBIOS CP | GAIT CP FW | Canada | alloc_CP | Incremental - XCHG |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [16 empty] | 8 | 1 | 30138.2495 | 241105.9961
PFO | Chris | SPG_VBIOS RLC | GAIT RLC FW | USA | alloc_RLC | Existing FTE |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
PFO | Chris | SPG_VBIOS RLC | GAIT RLC FW | China Shanghai | alloc_RLC | Incremental - XCHG |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [13 empty] | 13 | 1 | 27275.2088 | 354577.7147
Security | Hugo | SPG_Security | SDL | USA | alloc_Product Security | Existing - AOP |  |  |  | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | [13 empty] | 1.8 | 0.2 | 57001.2017 | 102602.1631
Security | Hugo | SPG_Security | FIPS certification | USA | alloc_Product Security | Existing - AOP |  |  |  |  | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | [13 empty] | 1.7 | 0.2 | 57001.2017 | 96902.0429
SW PM | Matthias | SPG_SW_ProgramManagers | Cross-Functional SW PM | Canada | alloc_Program Management_AlejandroR | Existing - AOP |  | 0.1 | 0.2 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.2 | [6 empty] | 0 | 0 |  |  |  |  | 6.1 | 0.5 | 30138.2495 | 183843.322
3DGFX | Rodney | SPG_ShaderCompiler | Lightning Compiler | USA | alloc_CG 3D Drivers And Compilers | Existing - AOP |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | 11 | 1 | 57001.2017 | 627013.219
Disp&MM | Syed | SPG_Display NPI | Charlie Wang | Canada | alloc_Display Solution_CharlieW | Incremental - XCHG |  |  |  | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | [13 empty] | 21 | 3 | 30138.2495 | 632903.2398
Disp&MM | Syed | SPG_Display NPI | Michael Vasnetsov | Canada | alloc_Display Solution_MazenS | Incremental - XCHG |  |  |  |  | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [13 empty] | 14 | 2 | 30138.2495 | 421935.4932
Disp&MM | Syed | SPG_VPE & DisplayNTI | Mazen Salloum | Canada | alloc_Display Solution_MazenS | Incremental - XCHG | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [16 empty] | 21 | 3 | 30138.2495 | 632903.2398
Disp&MM | Syed | SPG_MM Audio | ACP FW/ Driver | Taiwan | alloc_SWDEV_HYD_MM_Audio_NonWin | Incremental - XCHG |  |  |  |  | 2 | 2 | 2 | 3 | 4 | 4 | 3 | 2 | 1 | 1 | 0 | 0 | [12 empty] | 24 | 4 | 24974.5062 | 599388.1497
Disp&MM | Syed | SPG_MM Video NPI | Konstantin Moskvitin | Canada | alloc_mmdrivers_video_playback_pipelines | Incremental - XCHG | [5 empty] | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [13 empty] | 9 | 1 | 30138.2495 | 271244.2456
Disp&MM | Syed | SPG_MM Video NTI | Bill Li | Canada | alloc_mmdrivers_video_encode | Incremental - XCHG |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | [13 empty] | 14 | 1.5 | 30138.2495 | 421935.4932
PlatLinux | Chris | SPG_Platform_Linux | PreSI emulation | Canada | alloc_MLS_Linux_4 | Incremental - XCHG | [7 empty] | 1 | 1 | 1.5 | 0.5 | [17 empty] | 4 | 1.5 | 30138.2495 | 120552.9981
PlatLinux | Chris | SPG_Platform_Linux | NPI support(Linux Bringup (Silicon) with Base kernel) | Canada | alloc_MLS_Linux_4 | Incremental - XCHG | [8 empty] | 0.5 | 1 | 2 | 1.5 | 1.5 | 0.5 | [14 empty] | 7 | 2 | 30138.2495 | 210967.7466
PlatLinux | Chris | SPG_Platform_Linux | - Mesa, OpenGL 4.6, OpenGL ES 3.2, Vulkan-1.4 (Baremetal issue debug) | Canada | alloc_MLS_Linux_4 | Incremental - XCHG | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | [11 empty] | 4.1 | 0.5 | 30138.2495 | 123566.823
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
Terms of Reference |  |  |  |  | HC Profile | Existing - AOP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Existing - AOP |  | Existing resources already hired, AOP funded on a permanent basis |  |  |  | Incremental - XCHG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 0.5 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1 | 3 | 30138.2495 | 455087.5677
|  | e.g. HC_REG, HC_TEM, HC_COO, HC_CON, Commit - Co-Op |  |  |  | Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 2 | 2 | 1 | 0.5 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1 | 3 | 30138.2495 | 455087.5677
[5 empty] | Cost Profile ($M) | Existing - AOP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
Incremental - XCHG |  | Incremental resources request for HC, XCHG funded (typical) on a temporary basis |  |  |  | Incremental - XCHG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30138.2495 | 60276.499 | 90414.7485 | 90414.7485 | 60276.499 | 60276.499 | 30138.2495 | 15069.1248 | 9041.4749 | 9041.4749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 455087.5677
|  | e.g. Gaps, Non-HC - SPW, Outside Services (OSS) |  |  |  | Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30138.2495 | 60276.499 | 90414.7485 | 90414.7485 | 60276.499 | 60276.499 | 30138.2495 | 15069.1248 | 9041.4749 | 9041.4749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 455087.5677
[5 empty] | Adjustment | Incremental HC delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | -1 | 0 | -1 | -0.5 | -0.2 | 0 | -0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Scenarios | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change |  |  |  | No Change
[6 empty] | Adjustment (HC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
[6 empty] | New Incr. Cost ($M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30138.2495 | 60276.499 | 90414.7485 | 90414.7485 | 60276.499 | 60276.499 | 30138.2495 | 15069.1248 | 9041.4749 | 9041.4749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 455087.5677
[6 empty] | New Grand Total ($M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30138.2495 | 60276.499 | 90414.7485 | 90414.7485 | 60276.499 | 60276.499 | 30138.2495 | 15069.1248 | 9041.4749 | 9041.4749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 455087.5677

## Assumptions (PAVS)
Instructions: Please enter your function's name and capture assumptions applicable to your sizing
Team Name / Function | Scope / Deliverables | Assumptions | Risks
Platform Security FW | No PAVS Deliverables
SPG_MM_Audio | Scope of Work: • Reuse of Medusa ACP 7.3a (AAF2.0 & Client Linux leverage) • Delta: o SW ASILB support:  Audio chimes  ACP monitored by safety island o HW ASRC: Need to confirm with program – WIP. Note: For the base support we can leverage deliverables to automotive. FUSA and ASRC are prilim right now, will adjust the HC in future based on the final mPRS and the scope of FUSA work. | 1. SW ASILB & HW ASRC are required as per the priliminary understanding. 2. Legacy reuse
3D Graphics and Compiler Team |  | Assumptions: 1. We're moving forward with Open Sourced XGL & OGLP, which under Jeff W's organization instead of under Rodney's organization. 2. We're running this product on Linux & RTOS, no windows support for this program Therefore, there's no PAL work, no Graphics Compiler work, nor there is proprietary XGL & OGL work
SPG_Display NPI | Scope of Work (Linux Only): 1. RAS Features: . Virtual HW plane data path protection (based on the proposed solution from DCN HW team which need to be aligned with Embedded) . Increase ROI / pipe from 2 to 4 for DisplayCRC feature . Boot time display pipe stuck checking and reporting . Display pipe hang detection and reporting . Display data poison detection and reporting 2. DCN Linux kernel (within AMDGPU) and DCN FW for DCN RAS features are ASIL-B ready for certification (documentation, test coverage, coding standard) 3. (06/30) Added windows support leveraging common arch from linux with some delta work to power optimize video playback on windows | 1. The sizing does not include FuSA certification effort with FuSA accessors such as TÜV, SGS as it's customer solution end-to-end based 2. For RAS features which will report stuck/hang/poison, the assumption is the system need to decide what corrective action is needed to recover the hang. VPE/DCN just performs the reporting 3. Assumes work being done by KMD to enable the power optimized windows solution (Specifically: work for plumbing calls from DM/DC to enable work submission to VPE for queue/ctx mgmt, cmd submission, create fences, monitor fences)
SPG_MM_Video NPI | Leverage NVE version, that was bring up on Windows, is reused. NVE 1.3 will be used for Capitola. Capitola is the first to use this 1 core config of NVE NVE 1.3 FW and MMCore support for Linux upstream. Feature set scope is below: . HEVC / AVC / AV1 4:2:0 encode and decode . AV2 4:2:0 decode TBD . H.264 / H.265 4:2:2 encode and decode . H.264 / H.265 / AV2 4:4:4 encode and decode . Encode: Single-core, 4K-only . Decode: Single-core, 4K-only . No DCTD (no DNx decode) . No JPEG decode . No VPP . No MEE_ML . No MEE_Video | 1. Linux only 2. No RAS/ASILB for NVE
SPG_MM Video NTI | UES feature validation, bringup/debug support UES ASILB support for functinal safety | QoS policies is transparant to MM in the new internal VPE->DCN pipeline
RLC Firmware | No PAVS Deliverables
CP Firmware | No PAVS Deliverables
PMFW | No PAVS Deliverables
Core Linux | ROCm Support: - ROCm bringup on APU - ROCm Feats validation - KFD validation MM: - H264 and HEVC(Encode, Decode and Transcode) issue debug support. - NVE support BPI : 1. Build and Packaging 2. Separate Capitola branch creation. 3. Build script modifications if any. Linux IQE - Feature validation for ROCm/GFX/Display/MM/tools/Xen/ML Frameworks with Linux OS - Weekly integration test - Full cycle release test Graphics Virtualization - Guest Linux GPU recovery virtualization VirtIO GPU emulation - Xen/QEMU/Virglrenderer DOM0 (Graphics) VirtIO GPU emulation - Xen/QEMU/Virglrenderer DOM0 (Graphics - Windows) Graphics Virtualization - Guest Windows UMD (Virgl) Display Virtualization Display Virtualization (Windows) Graphics Virtualization - Guest Windows KMD Compute Virtualization - Guest ROCm (virtio-gpu) Compute Virtualization - Guest OpenCL (DOMU) Compute Virtualization - Host KFD multiple context Compute Virtualization - Guest HIP & Mathlib & Tools (DOMU) VirtIO GPU emulation - Xen/QEMU/Virglrenderer DOM0 (Compute) Cross functional team support/ Integrated Delivery Support DRM render node for ROCm virtualization Power Management Virtualization - Guest Graphics Virtualization - Guest Android (Issue Debugging Support) Linux - Solution Architect team | ROCm Support: - Validate the ROCm FEATs like KFD test, rocr test, roc profiler, roc gdb, rocminfo, clinfo, rocmruntime, OCL, etc MM: - Debug support is limited to H.264 and HEVC use cases, including Encode, Decode, and Transcode only. - VCN5 does not support YUV422 Subsampling format. So we don’t support this. - No new feature development is included as part of this scope. - GStreamer-based development or support is explicitly out of scope. - QT framework is out of scope. Linux IQE -Validation scope for ROCm stack is limited to KFD test/rocr test/rocprofiler/rocgdb/OCL - ML framework scope limited to Pytorch, Ollama.cpp, llama.cpp, vllm, NO performance validation -FuSa related features are out of this sizing scope -RAS validation is out of scope Linux: • Weston IVI is out of the scope. • Multidisplay is not scoped. • Dom0 and DomU should be in a display like Fairview Project. (One DOM0 + One DOMU in one single display). If requires more use cases, it need require CR. • Virtual primary plane is not scoped. • Functional safety (ASIL-B) for graphics driver and ROCm is not scoped. • P2P is not in scope. APU doesn’t support the P2P feature, so some IPC features cannot be enabled either. Windows: • Graphics Virtualization(UMD) → This phase provides a DirectX-10–based, GPU-accelerated Windows 10 desktop only. DX12, Windows 11, Vulkan, and Windows VM multimedia are explicitly out of scope. • No power management on Windows DOMU • Windows will not support vMPO/vPP, GPU timeout recovery. | No ASIL-B or ASIL-D efforts are estimated till we get the clear picture of usage on the UMD/D4KMD or ROCm side.
Advanced Technologies Group | -Program Management: Manage Capitola board delivery, Linux dependencies, Android bringup, xTS resolution -Architecture: Architecture support and technical guidance for Capitola platform - GNPU: Graphics performance analysis and ML workload analysis/optimization - Android VAS3.0: Deliver Android Automotive features -Robotics SW/Usecases: Deliver Robotics SW stack and end-customer use-cases including simulator HW acceleration - FuSA: ISO26262 functional safety guidance for ASIL-B compliance - DevOps + Validation/QA: Platform validation and quality assurance, CI build pipeline setup and maintenance | - HC sizing is based on analogous programs (Fairview, Glacier Peak, GLK) since specific use-cases aren't yet available - Component teams own UMD, Compiler, and KMD delivery - Component teams own FuSa ASIL-level scoping/sizing for their modules. ATG scoping constrained to guidance/consulting only - Balanced ownership of full system validation split between ATG and other teams | -Pre‑silicon VAS3.0 stack non-availability will delay Android bring‑up -Unclear validation ownership across teams -HC sizing uncertainty due to limited use‑case definition -Dependency risk from component team deliverables
SPG_SPIO | No PAVS Deliverables
Pre-Si FW Prg Mgr | No PAVS Deliverables

## Capitola C40 v1.0 r2 (PAVS)
Sizing is OPEN. Please UPDATE your estimates for your teams in this sheet. Also UPDATE the scope, assumptions and risks in the Assumptions tab. | [38 empty] | Status
Capitola C40 v1.0 r2 (PAVS) |  |  | Notes: BU - AECG - incorporate the updated R&R scope work-split with PAVS and G&E SW | [35 empty] | In Progress
Last Updated |  | 2026-06-22 | Schedule Milestones>> | [7 empty] | LSA | LSB | LSC | LSD | BTO | UU |  |  |  |  | IP
|  |  | Resource Allocation |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 170.5 | 24 | 10286.0833 | 4724862.1622
Category | Leader | Top Level Team | Function / Contact | Location | Allocation File | HC Type | Q126 | Q226 | Q326 | Q426 | Q127 | Q227 | Q327 | Q427 | Q128 | Q228 | Q328 | Q428 | Q129 | Q229 | Q329 | Q429 | Q130 | Q230 | Q330 | Q430 | Q131 | Q231 | Q331 | Q431 | Q132 | Q232 | Q332 | Q432 | Sum HC | Peak HC | Rate | Cost | HC Profile (mini) | Check
ATG | Chris | SPG_ADV Technology | Program Management | Canada | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | 12 | 1 | 30138.2495 | 361658.9942
ATG | Chris | SPG_ADV Technology | Architecture/Technical Lead | Canada | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | 12 | 1 | 30138.2495 | 361658.9942
ATG | Chris | SPG_ADV Technology | GNPU - Model enablement/perf optimization | Canada | alloc_PPL_ATG | Incremental - XCHG | [5 empty] | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | [12 empty] | 40 | 4 | 30138.2495 | 1205529.9806
ATG | Chris | SPG_ADV Technology | Android VAS3.0 - Video | Canada | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 1 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | [12 empty] | 31 | 4 | 30138.2495 | 934285.735
ATG | Chris | SPG_ADV Technology | Android VAS3.0 - Graphics/Display | Canada | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | [12 empty] | 27 | 3 | 30138.2495 | 813732.7369
ATG | Chris | SPG_ADV Technology | Android VAS3.0 - Security | Canada | alloc_PPL_ATG | Incremental - XCHG | [5 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | [12 empty] | 19 | 2 | 30138.2495 | 572626.7408
ATG | Chris | SPG_ADV Technology | Android VAS3.0 - Android Framework | Canada | alloc_PPL_ATG | Incremental - XCHG | [5 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | [12 empty] | 19 | 2 | 30138.2495 | 572626.7408
ATG | Chris | SPG_ADV Technology | Heterogeneous Compute Acceleration (CPU/GPU/GNPU) | Canada | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 2 | 4 | 6 | 4 | 8 | 8 | 8 | 8 | 6 | 6 | 4 | [12 empty] | 65 | 8 | 30138.2495 | 1958986.2185
ATG | Chris | SPG_ADV Technology | ROCm on Android/Virtualization | Canada | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | [12 empty] | 35 | 4 | 30138.2495 | 1054838.733
ATG | Chris | SPG_ADV Technology | FuSA consulting/support | Canada | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | 12 | 1 | 30138.2495 | 361658.9942
ATG | Chris | SPG_ADV Technology | Validation QA + DevOps | Canada | alloc_PPL_ATG | Incremental - XCHG |  |  |  | 1 | 2 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | [12 empty] | 44 | 5 | 30138.2495 | 1326082.9787
PlatLinux | Chris | SPG_Platform_Linux | Linux - KFD KGD ROCr/Thunk on Baremetal/PM/SMI/MM/BPI | Canada | alloc_MLS_Linux_4 | Incremental - XCHG |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | [11 empty] | 26 | 2 | 30138.2495 | 783594.4874
PlatLinux | Chris | SPG_Platform_Linux | Linux Dev /Virtualization/ROCm DOMU/IQE | China Shanghai | alloc_MLS_Linux_3 | Incremental - XCHG |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 9 | 10 | 13 | 13 | 13 | 11 | 9 | 6 | [11 empty] | 87.5 | 13 | 27275.2088 | 2386580.7719
PlatLinux | Chris | SPG_Platform_Linux | VirtIO GPU emulation - Xen/QEMU/Virglrenderer DOM0 (Graphics - Windows) | China Shanghai | alloc_MLS_Linux_3 | Incremental - XCHG | [9 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | [11 empty] | 12 | 2 | 27275.2088 | 327302.5059
PlatLinux | Chris | SPG_Platform_Linux | Display Virtualization (Windows) | China Shanghai | alloc_MLS_Linux_3 | Incremental - XCHG | [9 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | [11 empty] | 7 | 1 | 27275.2088 | 190926.4618
PlatLinux | Chris | SPG_Platform_Linux | Graphics Virtualization - Guest Windows KMD | China Shanghai | alloc_MLS_Linux_3 | Incremental - XCHG | [9 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | [11 empty] | 12 | 2 | 27275.2088 | 327302.5059
PlatLinux | Chris | SPG_Platform_Linux | Graphics Virtualization - Guest Windows UMD (Virgl) | China Shanghai | alloc_MLS_Linux_3 | Incremental - XCHG | [9 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | [11 empty] | 7 | 1 | 27275.2088 | 190926.4618
PlatLinux | Chris | SPG_Platform_Linux | Graphics Virtualization - Guest Android (Issue Debugging Support) | China Shanghai | alloc_MLS_Linux_3 | Incremental - XCHG | [9 empty] | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | [11 empty] | 19 | 3 | 27275.2088 | 518228.9676
Disp&MM | Syed | SPG_Display NPI | Charlie Wang | Canada | alloc_Display Solution_CharlieW | Incremental - XCHG | [8 empty] | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | [12 empty] | 17 | 3 | 30138.2495 | 512350.2418
[29 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
Terms of Reference |  |  |  |  | HC Profile | Existing - AOP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Existing - AOP |  | Existing resources already hired, AOP funded on a permanent basis |  |  |  | Incremental - XCHG | 0 | 0 | 0.5 | 1.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 15 | 17 | 23 | 24 | 24 | 22 | 18 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.5 | 24 | 27711.8015 | 4724862.1622
|  | e.g. HC_REG, HC_TEM, HC_COO, HC_CON, Commit - Co-Op |  |  |  | Grand Total | 0 | 0 | 0.5 | 1.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 15 | 17 | 23 | 24 | 24 | 22 | 18 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.5 | 24 | 27711.8015 | 4724862.1622
[5 empty] | Cost Profile ($M) | Existing - AOP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
Incremental - XCHG |  | Incremental resources request for HC, XCHG funded (typical) on a temporary basis |  |  |  | Incremental - XCHG | 0 | 0 | 13637.6044 | 43775.8539 | 73914.1034 | 73914.1034 | 73914.1034 | 73914.1034 | 73914.1034 | 414854.2137 | 469404.6314 | 633055.8843 | 660331.0931 | 660331.0931 | 605780.6755 | 496679.8402 | 357440.7554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4724862.1622
|  | e.g. Gaps, Non-HC - SPW, Outside Services (OSS) |  |  |  | Grand Total | 0 | 0 | 13637.6044 | 43775.8539 | 73914.1034 | 73914.1034 | 73914.1034 | 73914.1034 | 73914.1034 | 414854.2137 | 469404.6314 | 633055.8843 | 660331.0931 | 660331.0931 | 605780.6755 | 496679.8402 | 357440.7554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4724862.1622
[5 empty] | Adjustment | Incremental HC delta | 0 | 0 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 12.5 | 2 | 6 | 1 | 0 | -2 | -4 | -5 | -13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Scenarios | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change |  |  |  | No Change
[6 empty] | Adjustment (HC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
[6 empty] | New Incr. Cost ($M) | 0 | 0 | 13637.6044 | 43775.8539 | 73914.1034 | 73914.1034 | 73914.1034 | 73914.1034 | 73914.1034 | 414854.2137 | 469404.6314 | 633055.8843 | 660331.0931 | 660331.0931 | 605780.6755 | 496679.8402 | 357440.7554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4724862.1622
[6 empty] | New Grand Total ($M) | 0 | 0 | 13637.6044 | 43775.8539 | 73914.1034 | 73914.1034 | 73914.1034 | 73914.1034 | 73914.1034 | 414854.2137 | 469404.6314 | 633055.8843 | 660331.0931 | 660331.0931 | 605780.6755 | 496679.8402 | 357440.7554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4724862.1622

## Capitola C40 v1.0 r1
Sizing is CLOSED. This sheet is LOCKED and PROTECTED from editing. NO CHANGES are permitted while locked. Please contact Sam Huynh if you need to make any modifications. | [38 empty] | Status
Capitola C40 v1.0 r1 |  |  | Notes: BU - AECG REFERENCE ONLY - DO NOT EDIT OR MAKE CHANGES TO THIS SIZING | [35 empty] | Complete
Last Updated |  | 2026-05-26 | Schedule Milestones>> | [7 empty] | LSA | LSB | LSC | LSD | BTO | UU |  |  |  |  | IP
|  |  | Resource Allocation |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 634.6 | 76 | 16666.5385 | 19038734.6885
Category | Leader | Top Level Team | Function / Contact | Location | Allocation File | HC Type | Q126 | Q226 | Q326 | Q426 | Q127 | Q227 | Q327 | Q427 | Q128 | Q228 | Q328 | Q428 | Q129 | Q229 | Q329 | Q429 | Q130 | Q230 | Q330 | Q430 | Q131 | Q231 | Q331 | Q431 | Q132 | Q232 | Q332 | Q432 | Sum HC | Peak HC | Rate | Cost | HC Profile (mini) | Check
ATG | Chris | SPG_ADV Technology | Program Management | Global | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | 12 | 1 | 31000 | 372000
ATG | Chris | SPG_ADV Technology | Architecture/Technical Lead | Global | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | 12 | 1 | 31000 | 372000
ATG | Chris | SPG_ADV Technology | GNPU - Model enablement/perf optimization | Global | alloc_PPL_ATG | Incremental - XCHG | [5 empty] | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | [12 empty] | 40 | 4 | 31000 | 1240000
ATG | Chris | SPG_ADV Technology | Android VAS3.0 - Video | Global | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 1 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | [12 empty] | 31 | 4 | 31000 | 961000
ATG | Chris | SPG_ADV Technology | Android VAS3.0 - Graphics/Display | Global | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | [12 empty] | 27 | 3 | 31000 | 837000
ATG | Chris | SPG_ADV Technology | Android VAS3.0 - Security | Global | alloc_PPL_ATG | Incremental - XCHG | [5 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | [12 empty] | 19 | 2 | 31000 | 589000
ATG | Chris | SPG_ADV Technology | Android VAS3.0 - Android Framework | Global | alloc_PPL_ATG | Incremental - XCHG | [5 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | [12 empty] | 19 | 2 | 31000 | 589000
ATG | Chris | SPG_ADV Technology | Heterogeneous Compute Acceleration (CPU/GPU/GNPU) | Global | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 2 | 4 | 6 | 4 | 8 | 8 | 8 | 8 | 6 | 6 | 4 | [12 empty] | 65 | 8 | 31000 | 2015000
ATG | Chris | SPG_ADV Technology | ROCm on Android/Virtualization | Global | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | [12 empty] | 35 | 4 | 31000 | 1085000
ATG | Chris | SPG_ADV Technology | FuSA consulting/support | Global | alloc_PPL_ATG | Incremental - XCHG |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | 12 | 1 | 31000 | 372000
ATG | Chris | SPG_ADV Technology | Validation QA + DevOps | Global | alloc_PPL_ATG | Incremental - XCHG |  |  |  | 1 | 2 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | [12 empty] | 44 | 5 | 31000 | 1364000
PFO | Chris | SPG_FWProgMgmt | Pre-Si Sys FW PM | Canada | alloc_PFO_PM_Arch | Incremental - XCHG |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [17 empty] | 9 | 1 | 30138.2495 | 271244.2456
PFO | Chris | SPG_Platform Security | UBU / LibROM | Canada | alloc_PSPSecurity_MKM | Incremental - XCHG |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [17 empty] | 7 | 1 | 30138.2495 | 210967.7466
PFO | Chris | SPG_Platform Security | ART FW / ASP FW / Manufacturing FW | Canada | alloc_PSPSecurity_MKM | Incremental - XCHG |  |  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [16 empty] | 15 | 2 | 30138.2495 | 452073.7427
PlatLinux | Chris | SPG_Platform_Linux | Linux-PreSilicon/Bringup/Mesa/PM/SMI | Canada | alloc_MLS_Linux_4 | Incremental - XCHG |  |  |  | 0.1 | 0.2 | 0.5 | 0.5 | 1 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 2 | 1 | [11 empty] | 36.3 | 5 | 30138.2495 | 1094018.4574
PlatLinux | Chris | SPG_Platform_Linux | Linux Dev & IQE/Virtualization/ROCm DOMU | China Shanghai | alloc_MLS_Linux_3 | Incremental - XCHG |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 9 | 10 | 13 | 13 | 13 | 11 | 9 | 6 | [11 empty] | 87.5 | 13 | 27275.2088 | 2386580.7719
PFO | Chris | SPG_PMFW | PMFW | Canada | alloc_PMFW | Incremental - XCHG |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [16 empty] | 27 | 3 | 30138.2495 | 813732.7369
PFO | Chris | SPG_SPIO | ICTFW | Canada | alloc_SPIO | Incremental - XCHG |  |  |  |  | 1.5 | 3 | 3 | 3 | 3 | 3 | 2.6667 | 2.5 | 0 | [15 empty] | 21.6667 | 3 | 30138.2495 | 652995.4062
PFO | Chris | SPG_SPIO | OpenSIL + PFQ | Canada | alloc_SPIO | Incremental - XCHG |  |  |  |  | 2 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 0.5 | 0.5 | 0.5 | [13 empty] | 35 | 4.5 | 30138.2495 | 1054838.733
PFO | Chris | SPG_SPIO | MEM + DF | Canada | alloc_SPIO | Incremental - XCHG |  |  |  |  | 4.3 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 3.8333 | 3.5 | [16 empty] | 34.1333 | 4.5 | 30138.2495 | 1028718.9168
PFO | Chris | SPG_VBIOS CP | GAIT CP FW | Canada | alloc_CP | Incremental - XCHG |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [16 empty] | 8 | 1 | 30138.2495 | 241105.9961
PFO | Chris | SPG_VBIOS RLC | GAIT RLC FW | China Shanghai | alloc_RLC | Incremental - XCHG |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | [13 empty] | 38 | 3 | 27275.2088 | 1036457.9352
Security | Hugo | SPG_Security | SDL | USA | alloc_Product Security | Existing - AOP |  |  |  | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | [13 empty] | 1.8 | 0.2 | 57001.2017 | 102602.1631
Security | Hugo | SPG_Security | FIPS certification | USA | alloc_Product Security | Existing - AOP |  |  |  |  | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | [13 empty] | 1.7 | 0.2 | 57001.2017 | 96902.0429
SW PM | Matthias | SPG_SW_ProgramManagers | Cross-Functional SW PM | Canada | alloc_Program Management_AlejandroR | Existing - AOP |  | 0.1 | 0.2 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.2 | [6 empty] | 0 | 0 |  |  |  |  | 6.1 | 0.5 | 30138.2495 | 183843.322
3DGFX | Rodney | SPG_ShaderCompiler | Lightning Compiler | USA | alloc_CG 3D Drivers And Compilers | Existing - AOP |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | 11 | 1 | 57001.2017 | 627013.219
Disp&MM | Syed | SPG_Display NPI | Charlie Wang | Canada | alloc_Display Solution_CharlieW | Incremental - XCHG |  |  |  | 2 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 4 | 3 | [13 empty] | 48 | 6 | 30138.2495 | 1446635.9767
Disp&MM | Syed | SPG_MM Audio | ACP FW/ Driver | Taiwan | alloc_SWDEV_HYD_MM_Audio_NonWin | Incremental - XCHG |  |  |  | 1 | 1 | 2 | 2 | 3 | 4 | 4 | 3 | 2 | 1 | 1 | 0 | 0 | [12 empty] | 24 | 4 | 24974.5062 | 599388.1497
Disp&MM | Syed | SPG_MM Video NPI | Konstantin Moskvitin | Canada | alloc_mmdrivers_video_playback_pipelines | Incremental - XCHG | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [13 empty] | 8 | 1 | 30138.2495 | 241105.9961
Disp&MM | Syed | SPG_MM Video NTI | Bill Li | Canada | alloc_mmdrivers_video_encode | Incremental - XCHG |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | [13 empty] | 14 | 1.5 | 30138.2495 | 421935.4932
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
[35 empty] | 0 | 0 | 0 | 0
Terms of Reference |  |  |  |  | HC Profile | Existing - AOP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Existing - AOP |  | Existing resources already hired, AOP funded on a permanent basis |  |  |  | Incremental - XCHG | 0 | 0 | 4.5 | 8.6 | 27.5 | 40 | 46 | 50.5 | 54.5 | 72 | 72 | 72.5 | 55.5 | 50.5 | 42.5 | 31 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634.6 | 72.5 | 30001.1577 | 19038734.6885
|  | e.g. HC_REG, HC_TEM, HC_COO, HC_CON, Commit - Co-Op |  |  |  | Grand Total | 0 | 0 | 4.5 | 8.6 | 27.5 | 40 | 46 | 50.5 | 54.5 | 72 | 72 | 72.5 | 55.5 | 50.5 | 42.5 | 31 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634.6 | 72.5 | 30001.1577 | 19038734.6885
[5 empty] | Cost Profile ($M) | Existing - AOP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
Incremental - XCHG |  | Incremental resources request for HC, XCHG funded (typical) on a temporary basis |  |  |  | Incremental - XCHG | 0 | 0 | 125601.4804 | 250030.0539 | 826536.9736 | 1209297.3459 | 1395297.3459 | 1534366.4707 | 1654919.4688 | 2165758.7437 | 2162895.703 | 2169375.7057 | 1657025.464 | 1502025.464 | 1266061.588 | 925753.3784 | 193789.5024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 19038734.6885
|  | e.g. Gaps, Non-HC - SPW, Outside Services (OSS) |  |  |  | Grand Total | 0 | 0 | 125601.4804 | 250030.0539 | 826536.9736 | 1209297.3459 | 1395297.3459 | 1534366.4707 | 1654919.4688 | 2165758.7437 | 2162895.703 | 2169375.7057 | 1657025.464 | 1502025.464 | 1266061.588 | 925753.3784 | 193789.5024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 19038734.6885
[5 empty] | Adjustment | Incremental HC delta | 0 | 0 | 4.5 | 4.1 | 18.9 | 12.5 | 6 | 4.5 | 4 | 17.5 | 0 | 0.5 | -17 | -5 | -8 | -11.5 | -24 | -7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Scenarios | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change | NC - No change |  |  |  | No Change
[6 empty] | Adjustment (HC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
[6 empty] | New Incr. Cost ($M) | 0 | 0 | 125601.4804 | 250030.0539 | 826536.9736 | 1209297.3459 | 1395297.3459 | 1534366.4707 | 1654919.4688 | 2165758.7437 | 2162895.703 | 2169375.7057 | 1657025.464 | 1502025.464 | 1266061.588 | 925753.3784 | 193789.5024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 19038734.6885
[6 empty] | New Grand Total ($M) | 0 | 0 | 125601.4804 | 250030.0539 | 826536.9736 | 1209297.3459 | 1395297.3459 | 1534366.4707 | 1654919.4688 | 2165758.7437 | 2162895.703 | 2169375.7057 | 1657025.464 | 1502025.464 | 1266061.588 | 925753.3784 | 193789.5024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 19038734.6885

## Pivot
Cost ($M) | HC Type
Leader | Existing - AOP | Incremental - XCHG | Grand Total
Chris |  | 19038734.6885 | 19038734.6885
Hugo | 199504.206 |  | 199504.206
Matthias | 183843.322 |  | 183843.322
Rodney | 627013.219 |  | 627013.219
Syed |  | 2709065.6158 | 2709065.6158
Grand Total | 1010360.7471 | 21747800.3043 | 22758161.0514

## StatusTracking
Team | Contact | Scope / Function / Impact / Involvement | Status | Comments

## BrowserTab
BROWSER VIEWING HAS BEEN DISABLED. PLEASE OPEN IN EXCEL DESKTOP APP TO USE THIS FILE. Click on the "Editing" button and select "Open in Desktop App"

## Instructions (hidden)
Instructions
Step | Description | Illustrations / Pictorials
1 | In column D, look for your top-level teams in column D
2 | In column E, type in your specific function or team name in column E, as needed (or leave blank)
3 | In column G, select the HC type (Existing, FTE, Contractor) via drop down list. Do not mix existing and new HC together, use separate rows Add new rows as needed
4 | In columns H through AA, fill in the HC estimate by quarter
5 | Enter in scope deliverables, assumptions, risks in the Assumptions tab for your respective team(s)

## LUT
Look up Table for teams/leaders/category |  |  | Lists for drop down menus | [5 empty] | CVP / Allocation Files drop down menus | [8 empty] | CVP / Top Level Teams drop down menus
Top Level | Leader | Category | Options | HC Type | Labour Rate | Location | Status | Note | CVP | Rodney | Chris | Hugo | Matthias | Stephen | Syed | Terry | Jeffrey | RodneyTeam | ChrisTeam | HugoTeam | MatthiasTeam | StephenTeam | SyedTeam | TerryTeam | JeffreyTeam
3D_Perf_Arch | Rodney | 3DGFX | choice 1 | Existing - AOP | 57001.2017 | USA |  |  | Chris | alloc_CG 3D Drivers And Compilers | alloc_BTSR | alloc_Product Security | alloc_CE Markham | alloc_SQA Client APU | alloc_Display Solution_AlexS | alloc_ux | alloc_Software Technologies | SPG_3D_ArchNPIPM | SPG_ADV Technology | SPG_Security | SPG_CSE_FirstPartner_Customer Engineering | SPG_SSE Infrastructure | SPG_Display NPI | SPG_Roadmap Installer User Experience | SPG_SW Technology
D3D | Rodney | 3DGFX | choice 2 | Incremental - XCHG | 30452.7636 | Bulgaria | Complete | Sizing is CLOSED. This sheet is LOCKED and PROTECTED from editing. NO CHANGES are permitted while locked. Please contact Sam Huynh if you need to make any modifications. | Hugo |  | alloc_CG 3D Drivers and Compilers |  | alloc_CSE_CEPM | alloc_SQA Core and Common Services | alloc_Display Solution_CharlieW |  |  | SPG_3D_CQE | SPG_FWProgMgmt |  | SPG_CSE_FirstPartner_FAST | SPG_SSE QA | SPG_MM Audio
HYD Graphics CQE | Rodney | 3DGFX | choice 3 |  | 30452.7636 | Greece | In Progress | Sizing is OPEN. Please UPDATE your estimates for your teams in this sheet. Also UPDATE the scope, assumptions and risks in the Assumptions tab. | Jeffrey |  | alloc_CP |  | alloc_CSE_CoreSW | alloc_SQA CVSAI | alloc_Display Solution_EricC |  |  | SPG_3D_Perf_Arch | SPG_Platform Security |  | SPG_Customer Eng | SPG_SSE RM | SPG_MM Video NPI
Khronos3D | Rodney | 3DGFX | choice 4 |  | 30452.7636 | Brazil | MS Project | Sizing is EXTRACTED from MS Project Server and COPIED here. NO CHANGES are permitted on this sheet. Please update the resource allocation files and publish them, data will be updated daily. | Matthias |  | alloc_MLS_Linux_1 |  | alloc_CSE_CPMCN | alloc_SQA GW dGPU | alloc_Display Solution_JagM |  |  | SPG_3D_PerfML | SPG_Platform SW Arch |  | SPG_Mac Platform |  | SPG_MM Video NTI
PAL | Rodney | 3DGFX | choice 5 |  | 30452.7636 | Mexico |  |  | Rodney |  | alloc_MLS_Linux_2 |  | alloc_CSE_CPMTW | alloc_SQA Product Support and Enablement | alloc_Display Solution_MazenS |  |  | SPG_3D_Tooling | SPG_Platform Virtualization |  | SPG_Operations |  | SPG_VPE & DisplayNTI
Shader Compilers | Rodney | 3DGFX | choice 6 |  | 30452.7636 | Argentina |  |  | Stephen |  | alloc_MLS_Linux_3 |  | alloc_CSE_Management | alloc_SQA Solutions | alloc_Display Solution_MichaelV |  |  | SPG_D3D | SPG_Platform Windows |  | SPG_SW_ProgramManagers
Shader Compilers – LLVM & SC | Rodney | 3DGFX | choice 7 |  | 30138.2495 | Canada |  |  | Syed |  | alloc_MLS_Linux_4 |  | alloc_CSE_Strategic | alloc_SWInfra_IND | alloc_Display Solution_NikolaC |  |  | SPG_HYD Graphics CQE | SPG_Platform_Linux
SPG_3D_Perf_Arch | Rodney | 3DGFX | choice 8 |  | 12203.0397 | India Hyderabad |  |  |  |  | alloc_OS_MUL_Security_Kernel_BLR |  | alloc_CSE_SWAE | alloc_swinfra_na | alloc_Display Solution_VladmirVelenta |  |  | SPG_Khronos3D | SPG_PMFW
SPG_3D_Tooling | Rodney | 3DGFX | choice 9 |  | 30452.7636 | Australia |  |  |  |  | alloc_PFO_PM_Arch |  | alloc_CSE_TL | alloc_swrelman | alloc_Display_MM_VP_Direct Reports |  |  | SPG_Mac 3D | SPG_SPIO
SPG_D3D | Rodney | 3DGFX | choice 10 |  | 26138.97 | Japan |  |  |  |  | alloc_Platform SW Arch |  | alloc_PMO Common_BrianW |  | alloc_Gaming_Engineering |  |  | SPG_PAL | SPG_VBIOS CP
SPG_HYD Graphics CQE | Rodney | 3DGFX |  |  | 24974.5062 | Taiwan |  |  |  |  | alloc_PMFW |  | alloc_PMO Common_PaulM |  | alloc_mmdrivers_video_encode |  |  | SPG_ShaderCompiler | SPG_VBIOS RLC
SPG_Khronos3D | Rodney | 3DGFX |  |  | 17893.5022 | Serbia |  |  |  |  | alloc_PPL_ATG |  | alloc_PMO Common_SharmilyB |  | alloc_mmdrivers_video_playback_pipelines |  |  |  | SPG_VBIOS VBL
SPG_Mac 3D | Rodney | 3DGFX |  |  | 53696.445 | France |  |  |  |  | alloc_PPL_Virtualization |  | alloc_PMO Common_VithalP |  | alloc_SWDEV_HYD_MM_Audio_NonWin
SPG_PAL | Rodney | 3DGFX |  |  | 35285.1407 | Germany |  |  |  |  | alloc_PSPSecurity_MKM |  | alloc_Program Management_AlejandroR |  | alloc_SWDEV_HYD_MM_Audio_Win
SPG_Shader Compilers | Rodney | 3DGFX |  |  | 41547.43 | Italy |  |  |  |  | alloc_RLC |  | alloc_Program Management_DerekY |  | alloc_SWDEV_HYD_MM_Video
SPG_ShaderCompiler | Rodney | 3DGFX |  |  | 50477.43 | Sweden |  |  |  |  | alloc_SPIO |  | alloc_Program Management_JonB
SPG_3D_ArchNPIPM | Rodney | 3DGFX |  |  | 55809.1144 | UK |  |  |  |  | alloc_VBL |  | alloc_Program Management_ReyE
SPG_3D_CQE | Rodney | 3DGFX |  |  | 39047.15 | Spain |  |  |  |  | alloc_VPs_DirectReports |  | alloc_Program Management_StefanT
ADV Technology | Chris | ATG |  |  | 25848.2362 | Poland |  |  |  |  | alloc_WSPG_BG_KMD_CORE |  | alloc_Program Management_SW Client and NOI
IPU Driver - Existing | Chris | ATG |  |  | 27870.18 | Netherlands |  |  |  |  | alloc_WSPG_BG_KMD_Hyderabad |  | alloc_Program Management_VioF
IPU Validation | Chris | ATG |  |  | 12203.0397 | India Bangalore |  |  |  |  | alloc_WSPG_BG_KMD_Solutions_CAN
Power/ Perf | Chris | ATG |  |  | 27275.2088 | China Shanghai |  |  |  |  | alloc_WSPG_BG_KMD_SRDC
SPG_ADV Technology | Chris | ATG |  |  | 27275.2088 | China Beijing and Shenzhen |  |  |  |  | alloc_WSPG_BG_Leadership
CSE_FirstPartner_CustEng | Matthias | CSE |  |  | 31000 | Global |  |  |  |  | alloc_WSPG_BG_System and Power
SPG_Customer Eng | Matthias | CSE | [8 empty] | alloc_WSPG_BG_Test and Tools
SPG_CSE_FirstPartner_CustEng | Matthias | CSE | [8 empty] | alloc_WSPG_MsftInterface
SPG_CSE_FirstPartner_Customer Engineering | Matthias | CSE | [8 empty] | alloc_WSPG_PM_TL
SPG_CSE_FirstPartner_FAST | Matthias | CSE | [8 empty] | alloc_WSPG_QE_Core
SPG_Customer_Eng | Matthias | CSE | [8 empty] | alloc_WSPG_QE_HYD
SPG_Mac Platform | Matthias | CSE | [8 empty] | alloc_WSPG_QE_MKM
Display NPI | Syed | Disp&MM | [8 empty] | alloc_WSPG_QE_SRDC
Display NTI | Syed | Disp&MM | [8 empty] | alloc_WSPG_QE_Stability_NTI
MM Audio | Syed | Disp&MM | [8 empty] | alloc_WSPG_QE_TnD_NOI
MM Video | Syed | Disp&MM
SPG_Display NPI | Syed | Disp&MM
SPG_Display NTI | Syed | Disp&MM
SPG_Display NTI - VPE | Syed | Disp&MM
SPG_MM Audio | Syed | Disp&MM
SPG_MM Video | Syed | Disp&MM
SPG_MM Video - UMSCH | Syed | Disp&MM
SPG_MM Video NPI | Syed | Disp&MM
SPG_MM Video NTI | Syed | Disp&MM
SPG_VPE & DisplayNTI | Syed | Disp&MM
FWProgMgmt | Chris | PFO
GFX-CP | Chris | PFO
GFX-RLC | Chris | PFO
PMFW | Chris | PFO
SMU | Chris | PFO
SPG_Architecture and Sys IP | Chris | PFO
SPG_FWProgMgmt | Chris | PFO
SPG_GFX-CP | Chris | PFO
SPG_GFX-RLC | Chris | PFO
SPG_IPU Driver - Existing | Chris | PFO
SPG_IPU Validation | Chris | PFO
SPG_PMFW | Chris | PFO
SPG_SMU | Chris | PFO
SPG_SPIO | Chris | PFO
SPG_VBIOS | Chris | PFO
SPG_VBIOS CP | Chris | PFO
SPG_VBIOS RLC | Chris | PFO
SPG_VBIOS VBL | Chris | PFO
SPIO | Chris | PFO
VBIOS | Chris | PFO
SPG_Platform SW Arch | Chris | PFO
Platform Security | Chris | PFO
SPG_Platform Security | Chris | PFO
Platform_Linux | Chris | PlatLinux
SPG_Platform_Linux | Chris | PlatLinux
KMD Solutions | Chris | PlatWin
KMD Test & Tools | Chris | PlatWin
PLAT Win: IQE/CQE | Chris | PlatWin
PLAT Win: KMD Core | Chris | PlatWin
PLAT Win: KMD Core MKM | Chris | PlatWin
PLAT Win: KMD Core SRDC | Chris | PlatWin
PLAT Win: KMD Solutions | Chris | PlatWin
PLAT Win: KMD Solutions HYD | Chris | PlatWin
PLAT Win: KMD Solutions MKM | Chris | PlatWin
PLAT Win: MS Interface | Chris | PlatWin
PLAT Win: PM/ SW TL / Arch | Chris | PlatWin
PLAT Win: System & Power | Chris | PlatWin
Platform Windows | Chris | PlatWin
SPG_Platform Windows | Chris | PlatWin
Security | Hugo | Security
SPG_Security | Hugo | Security
SPG_SSE QA | Stephen | SQA
SSE QA | Stephen | SQA
SPG_SSE Infrastructure | Stephen | SSE Infra
SSE Infrastructure | Stephen | SSE Infra
SPG_SSE RM | Stephen | SSE RM
SPG_Operations | Matthias | SW Ops
SPG_SW_ProgramManagers | Matthias | SW PM
SW_ProgramManagers | Matthias | SW PM
SPG_Roadmap Installer User Experience | Terry | UX
Platform Virtualization | Chris | Virtualization
SPG_Platform Virtualization | Chris | Virtualization

## Ramp Scenarios (hidden)
Scenarios | Cost Factor | M1 | M2 | M3 | Ramp Curve
NC - No change | 1 | 100 | 100 | 100
90% | 0.9 | 90 | 90 | 90
80% | 0.8 | 80 | 80 | 80
70% | 0.7 | 70 | 70 | 70
60% | 0.6 | 60 | 60 | 60
50% | 0.5 | 50 | 50 | 50
40% | 0.4 | 40 | 40 | 40
20% | 0.2 | 20 | 20 | 20
OMIT - remove | 0 | 0 | 0 | 0